|  |  |  |
| --- | --- | --- |
| **TIME BEFORE REGATTA START**  | **EVENT**  | **REGATTA REGULATIONS REFERENCE**  |
| 48 mo.  | Proposal submitted by host country to IJCA World Council  | GENERAL 3. WORLDS 1.  |
| 47 mo.  | Host country forms World Championship Organizing Committee  | WORLDS 2.  |
| 46 mo.  | Commitment by host NJCA to sign Agreement with IJCA  | WORLDS 1.3 APPENDIX I  |
| 45 mo.  | Agreement signed between World Championship Organizing Committee, host NJCA and the IJCA.  | WORLDS 2.5  |
| 36 mo.  | Written plan and progress report submitted to the IJCA World Council  |  |
| 24 mo.  | Progress report submitted to the IJCA World Council  |  |
| 18 mo.  | Jury and Principal Race Officer invited and conﬁrmed  | WORLDS 3.1, 3.2  |
| 12 mo.  | IJCA Chairman to inspect the Worlds regatta site.  | Agreement 6.  |
| 12 mo.  | Notice of Race to be submitted to the IJCA Class Office for approval by the IJCA Technical and Executive Committees  | WORLDS 7.4  |
| 6 mo.  | Sailing Instructions to be submitted to the IJCA Class Office for approval by the IJCA Technical and Executive Committees  | WORLDS 8.5  |
| 120 days  | IJCA Exec. Dir. to inform NJCAs of eligible entries and send the OA a list of Automatic Qualiﬁers  | WORLDS 4, 5.6  |
| 120 days  | Last date for completion of Worlds Qualifying Events by NJCAs  | WORLDS 5.1  |
| 90 days  | Last day for NJCAs to submit World Qualifying helmspersons’ names to the IJCA Class Office  | WORLDS 5.6  |