|  |  |  |
| --- | --- | --- |
| **TIME BEFORE REGATTA START** | **EVENT** | **REGATTA REGULATIONS REFERENCE** |
| 48 mo. | Proposal submitted by host country to IJCA World Council | GENERAL 3. WORLDS 1. |
| 47 mo. | Host country forms World Championship Organizing Committee | WORLDS 2. |
| 46 mo. | Commitment by host NJCA to sign Agreement with IJCA | WORLDS 1.3 APPENDIX I |
| 45 mo. | Agreement signed between World Championship Organizing Committee, host NJCA and the IJCA. | WORLDS 2.5 |
| 36 mo. | Written plan and progress report submitted to the IJCA World Council |  |
| 24 mo. | Progress report submitted to the IJCA World Council |  |
| 18 mo. | Jury and Principal Race Officer invited and conﬁrmed | WORLDS 3.1, 3.2 |
| 12 mo. | IJCA Chairman to inspect the Worlds regatta site. | Agreement 6. |
| 12 mo. | Notice of Race to be submitted to the IJCA Class Office for approval by the IJCA Technical and Executive Committees | WORLDS 7.4 |
| 6 mo. | Sailing Instructions to be submitted to the IJCA Class Office for approval by the IJCA Technical and Executive Committees | WORLDS 8.5 |
| 120 days | IJCA Exec. Dir. to inform NJCAs of eligible entries and send the OA a list of Automatic Qualiﬁers | WORLDS 4, 5.6 |
| 120 days | Last date for completion of Worlds Qualifying Events by NJCAs | WORLDS 5.1 |
| 90 days | Last day for NJCAs to submit World Qualifying helmspersons’ names to the IJCA Class Office | WORLDS 5.6 |